✦  SEQUINS

Product Roadmap & Launch Strategy

Internal Document  ·  Prepared June 09, 2026

PHASE 0 — Foundation    [COMPLETE]

Everything in this phase is shipped and in the repository.

CORE APP INFRASTRUCTURE

✓  Expo SDK 54 / React Native app with Expo Router file-based navigation

✓  Tab navigation: Discover, Tickets, Create, Performers, Profile

✓  Supabase backend: PostgreSQL database, Auth, Storage, Edge Functions

✓  Email / magic-link authentication + guest (browse-only) mode

✓  Deep-link handler for auth callbacks (password reset, email confirmation)

✓  Role system: Host · Performer · Attendee — onboarding flow per role

✓  Splash screen, dark navy/teal theme, DismissKeyboard wrapper

EVENTS

✓  Event creation with title, description, date/time, venue, recurring flag

✓  Event image upload to Supabase Storage

✓  Discovery feed with promoted-event badge, search/filter

✓  Event detail page: performers, ticketing card, host info

✓  Host event management (edit, cancel)

PERFORMERS

✓  Performer profile creation: stage name, bio, commission types, photo

✓  Performer directory & public profile page

✓  Performer photo upload to Supabase Storage (non-fatal on RLS)

TICKETING & PAYMENTS

✓  Free ticket reservation flow

✓  Paid ticket flow via Stripe (payment sheet, navy/teal theme)

✓  Stripe Edge Function (create-payment-intent) deployed to Supabase

✓  Ticket list in Profile tab, ticket detail view

✓  Host notified on ticket sale (in-app notification)

✓  Door check-in flow (ticket scan / manual lookup)

NOTIFICATIONS & ANDROID POLISH

✓  In-app notifications store + bell icon with unread badge

✓  KeyboardAvoidingView / textAlignVertical Android fixes

✓  edgeToEdgeEnabled Android config

✓  Guest mode session-only (no AsyncStorage persistence)

PHASE 1 — Beta Ready    [IN PROGRESS]

Goal: app is testable on real devices with real data. Target: Q3 2026.

PUSH NOTIFICATIONS (DEVICE)

•  Install expo-notifications, request device permissions on first launch

•  Store Expo push token in Supabase user profile

•  Edge Function: send push notification via Expo Push API

•  Wire existing notification events (ticket sold, new follower, event update) to push

STRIPE — FINISH LINE

•  Add sequins:// to Supabase Dashboard → Auth → URL Configuration → Redirect URLs

•  Run storage RLS SQL migration (performer-photos & event-images buckets)

•  Test full paid ticket flow with card 4242 4242 4242 4242

•  Swap pk_test_ / sk_test_ for live keys when ready for real payments

REAL EVENT DATA

•  Seed ~20 real/realistic drag events across Portland, Seattle, Kansas City, St. Petersburg FL

•  Source real venue names, event fliers / promo photos, performer names

•  Data presentable for pitching to queens and hosts

APP STORE ACCOUNTS

•  Apple Developer Program ($99/yr) — apply after LLC/EIN are confirmed

•  App Store Connect: bundle ID app.sequins, screenshots, metadata (docs already written)

•  Google Play Developer ($25 one-time) — can register before Apple if needed

•  Google Play Console: create app, upload AAB, fill store listing

QA & POLISH

•  Regression test all 10 Android/iOS cross-platform bugs fixed in last sprint

•  Performance audit: Discovery feed load time, image caching

•  Crash logging setup (Sentry or Expo error reporting)

PHASE 2 — Community Features    [PLANNED]

Goal: features that keep people coming back. Target: Q4 2026.

IN-APP MESSAGING

•  Direct messages between Hosts, Performers, and Attendees

•  Message threads stored in Supabase (messages table + RLS)

•  Realtime updates via Supabase Realtime subscriptions

•  Push notification on new message

•  Conversation list in Profile tab with unread badge

SOCIAL MEDIA PROFILE LINKING

•  Performer/Host profile: link Instagram, TikTok, Facebook, Twitter/X

•  Store social handles in profiles table

•  Display as tappable icons on public profile pages (deep link to app)

LGBTQ+ SAFE LOCATIONS DIRECTORY

•  Safe spaces map/list: bars, community centers, health clinics, shelters

•  Seed data for Oregon, Washington, Florida, California, Kansas

•  Source via Google Places API or manual curation from The Safe Zone Project / GLSEN

•  Filterable by type: bar, clinic, shelter, community center, bookstore

•  User can suggest new locations (goes into moderation queue)

CONTENT MODERATION

•  Report button on events, performer profiles, and future messages

•  Moderation queue in a web admin panel (Supabase Studio or custom)

•  Auto-suspend on 3+ reports pending review

•  Admin role: can delete events, ban users, approve suggested locations

•  Community guidelines displayed in onboarding

AUTOMATED TESTING

•  Unit tests: Jest for store functions (authStore, ticketStore, eventsStore)

•  Component tests: React Native Testing Library for key screens

•  E2E smoke tests: Detox for critical paths (sign-up, buy ticket, create event)

•  CI: GitHub Actions running tests on every pull request

HOST TOOLS

•  Host dashboard: ticket sales count, revenue, check-in rate per event

•  Export attendee list (CSV) for door staff

•  Co-host / staff roles for larger events

PHASE 3 — Soft Launch    [PLANNED]

Goal: real queens, real shows, real feedback. Target: end of 2026.

BETA PROGRAM

•  Invite 10-20 queens from Portland, Seattle, Kansas City, St. Petersburg FL

•  Private TestFlight (iOS) + internal track (Google Play) builds

•  Feedback survey after 2 weeks of use

•  Iterate on top 5 feedback items before public launch

APP STORE SUBMISSION

•  Submit to Apple App Store review (allow 1-2 week review window)

•  Submit to Google Play review (typically 3-7 days)

•  Respond to any reviewer feedback / rejection reasons

•  Both stores approved and live

STRIPE LIVE MODE

•  Complete Stripe account verification (business details, banking)

•  Swap test keys for live keys in .env and Supabase secrets

•  Run one real $1 test transaction end-to-end

•  Set up Stripe webhook for payment_intent.succeeded (refund safety net)

MARKETING FOUNDATION

•  QR code cards printed and in the hands of beta queens

•  Sequins landing page live on thebradleyproject.com/sequins

•  Instagram account created for Sequins (@sequinsapp or similar)

•  Short demo video / screen-record for pitching

PHASE 4 — Pride 2027 Push    [FUTURE]

Goal: max visibility at Pride season. Target: June 2027.

PUBLIC LAUNCH

•  App Store + Google Play fully public, all ages

•  Promoted events monetization fully live (host pays to boost)

•  Sequins featured in LGBTQ+ app directories and press

PRIDE EVENT SEEDING

•  Partner with Pride orgs: Portland Pride, Seattle Pride, Tampa Pride, Kansas City Pride

•  All major Pride weekend events listed and ticketed inside Sequins

•  Volunteer or comp tickets for queens who bring audiences onto the platform

GROWTH & PARTNERSHIPS

•  Outreach to bars and venues in each target city for venue partnerships

•  Performer booking flow: Hosts can book Performers through the app

•  Press outreach: LGBTQ+ media, local alt-weeklies

•  Goal: 500 registered users, 50 active performers, 20 ticketed events by Pride 2027

PLATFORM HEALTH

•  Analytics dashboard: DAU, MAU, ticket volume, revenue

•  Abuse/moderation metrics reviewed weekly

•  Performance SLA: Discovery feed loads in < 1.5s on LTE

QUICK REFERENCE TIMELINE

| Phase | Status | Target | Key Win |
| --- | --- | --- | --- |
| Phase 0 — Foundation | ✓ Complete | Done | App runs on iOS & Android |
| Phase 1 — Beta Ready | ↻ In Progress | Q3 2026 | Push notifs, real data, Stripe live |
| Phase 2 — Community | Planned | Q4 2026 | Messaging, safe spaces, moderation |
| Phase 3 — Soft Launch | Planned | Dec 2026 | Queens testing, App Stores live |
| Phase 4 — Pride Push | Future | June 2027 | Public launch, Pride partnerships |

CONFIDENTIAL — INTERNAL USE ONLY  ·  Sequins App  ·  2026